## Sprint 2
Team 1 - Tasks for User Stories - BulkCart
Task No. | Module | RCT ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Task Type | Crosscut Reference | Start Date | End Date | % Progress | Owner
1 | 02. Order & Approval Management | 02.03 | Track Order Status & History | Design order status timeline UI showing status stages (Submitted, Approved, Shipped, Delivered) | Y | Development | ET-In, ET-Ex | 2026-03-25 | 2026-03-25 | 100% | Aakash Hariprakash Varma
2 |  |  |  | Implement API calls to fetch order history and status updates per order ID | Y | Development | DF-In | 2026-03-26 | 2026-03-27 | 100% | Kiran Subhash Rathod
3 |  |  |  | Restrict order history visibility to the retailer who placed the order and their manager | Y | Development | ET-Ex | 2026-03-28 | 2026-03-28 | 100% | Arun Omprakash Garwan
4 |  |  |  | Test status transitions and audit log entries for each order stage change | N | Testing | ADT | 2026-03-28 | 2026-03-29 | 100% | Vivek Vekhande
5 |  | 02.04 | Order Drafts & Editing | Build draft order saving UI with auto-save and manual save options | Y | Development | ET-In, ET-Ex | 2026-03-29 | 2026-03-30 | 100% | Aakash Hariprakash Varma
6 |  |  |  | Implement draft retrieval and edit flow; recalculate totals on edit (quantities, pricing) | Y | Development | DF-In, DF-Out, CL | 2026-03-30 | 2026-03-31 | 100% | Meet Pravinbhai Mangukiya
7 |  |  |  | Validate required fields before allowing draft submission; block invalid quantities | Y | Development | FV | 2026-03-31 | 2026-03-31 | 100% | Kiran Subhash Rathod
8 |  |  |  | Test draft save, load, edit, and submit flow; verify audit trail entries on each action | N | Testing | ADT | 2026-04-01 | 2026-04-01 | 100% | Om Kiran Patil
9 |  | 02.05 | Order Validation & Business Rules | Implement business rule engine: check minimum order quantities, credit limit, and supplier policy constraints | Y | Development | FV, CL | 2026-04-01 | 2026-04-02 | 100% | Arun Omprakash Garwan
10 |  |  |  | Integrate validation with order submission flow; block or warn on rule violations | Y | Development | DF-In, DF-Out | 2026-04-02 | 2026-04-02 | 100% | Kiran Subhash Rathod
11 |  |  |  | Apply entitlement checks — only authorized roles can override validation warnings | Y | Development | ET-In, ET-Ex | 2026-04-03 | 2026-04-03 | 100% | Aakash Hariprakash Varma
12 |  |  |  | Test validation rules for edge cases: zero quantities, over-credit, policy exceptions; verify audit logs | N | Testing | ADT | 2026-04-03 | 2026-04-03 | 100% | Asmith Reddy Mamilla
13 |  | 02.06 | Order Search & Filtering | Build order search and filter UI (by supplier, date range, status, order ID) | Y | Development | ET-In, ET-Ex | 2026-04-04 | 2026-04-05 | 100% | Aakash Hariprakash Varma
14 |  |  |  | Validate filter inputs and handle empty result states gracefully | Y | Development | FV | 2026-04-05 | 2026-04-05 | 100% | Arun Omprakash Garwan
15 |  |  |  | Test search results accuracy and entitlement — retailer only sees their own orders | N | Testing | ADT | 2026-04-06 | 2026-04-06 | 100% | Vivek Vekhande
16 |  | 02.07 | Bulk Order Processing | Design bulk order import UI and template (CSV/Excel upload with field mapping) | Y | Development | ET-In, ET-Ex | 2026-04-06 | 2026-04-07 | 100% | Kiran Subhash Rathod
17 |  |  |  | Parse and validate uploaded bulk order file; calculate line totals and order summary | Y | Development | FV, CL, DF-In | 2026-04-07 | 2026-04-08 | 100% | Meet Pravinbhai Mangukiya
18 |  |  |  | Submit validated bulk orders to backend and emit order confirmation data-out | Y | Development | DF-Out | 2026-04-08 | 2026-04-08 | 100% | Arun Omprakash Garwan
19 |  |  |  | Test bulk upload with valid, partial, and fully invalid files; verify audit log per submission | N | Testing | ADT | 2026-04-09 | 2026-04-09 | 100% | Om Kiran Patil
20 | 03. Product Catalog & Pricing | 03.01 | Manage Product Catalog & Inventory | Build supplier product management UI: add/edit SKUs, descriptions, units, categories, and images | Y | Development | ET-In, ET-Ex | 2026-04-09 | 2026-04-10 | 100% | Aakash Hariprakash Varma
21 |  |  |  | Implement product catalog API calls (create, update, delete SKUs); sync with inventory system (SI) | Y | Development | DF-In, DF-Out, SI | 2026-04-10 | 2026-04-11 | 100% | Kiran Subhash Rathod
22 |  |  |  | Validate required product fields (name, SKU, unit, price > 0); block duplicate SKU submission | Y | Development | FV | 2026-04-11 | 2026-04-11 | 100% | Arun Omprakash Garwan
23 |  |  |  | Test catalog CRUD operations, image uploads, and audit trail for all catalog changes | N | Testing | ADT | 2026-04-12 | 2026-04-12 | 100% | Asmith Reddy Mamilla
24 |  | 03.02 | Configure Pricing & Discounts | Design pricing configuration UI: base price, volume tiers, and customer-specific price lists | Y | Development | ET-In, ET-Ex | 2026-04-12 | 2026-04-13 | 100% | Aakash Hariprakash Varma
25 |  |  |  | Implement pricing calculation logic for volume breaks and customer-specific overrides | Y | Development | CL, DF-In, DF-Out | 2026-04-13 | 2026-04-14 | 100% | Meet Pravinbhai Mangukiya
26 |  |  |  | Validate pricing inputs: price > 0, tier thresholds non-overlapping, discount % in range | Y | Development | FV | 2026-04-14 | 2026-04-14 | 100% | Kiran Subhash Rathod
27 |  |  |  | Test pricing rules, volume discount calculations, and audit log for every price change | N | Testing | ADT | 2026-04-15 | 2026-04-15 | 100% | Vivek Vekhande
28 |  | 03.03 | Browse & Search Product Catalog | Build retailer-facing product catalog browse UI with search bar, category filter, and product cards | Y | Development | ET-In, ET-Ex | 2026-04-15 | 2026-04-16 | 100% | Arun Omprakash Garwan
29 |  |  |  | Integrate product search API and external inventory system (SI) for real-time availability display | Y | Development | DF-In, SI | 2026-04-16 | 2026-04-17 | 100% | Kiran Subhash Rathod
30 |  |  |  | Validate search inputs and filter combinations; handle empty and error states | Y | Development | FV | 2026-04-17 | 2026-04-17 | 100% | Aakash Hariprakash Varma
31 |  |  |  | Test search accuracy, product visibility per retailer entitlement, and audit log on catalog views | N | Testing | ADT | 2026-04-18 | 2026-04-18 | 100% | Om Kiran Patil
32 | 05. Financial & Analytics | 05.02 | Process Payments | Build payment flow UI: show invoice, amount due, and payment method selection for retailers | Y | Development | ET-In, ET-Ex | 2026-04-19 | 2026-04-19 | 100% | Aakash Hariprakash Varma
33 |  |  |  | Integrate payment gateway API (SI): initiate payment, capture response, and update payment status | Y | Development | DF-In, DF-Out, SI | 2026-04-20 | 2026-04-21 | 100% | Kiran Subhash Rathod
34 |  |  |  | Calculate payment totals including taxes; validate payment amounts match invoice balance | Y | Development | FV, CL | 2026-04-21 | 2026-04-21 | 100% | Meet Pravinbhai Mangukiya
35 |  |  |  | Test successful payment, failed transaction, and partial payment; verify audit log and status updates | N | Testing | ADT | 2026-04-21 | 2026-04-21 | 100% | Vivek Vekhande
36 |  | 05.03 | Generate Spending Reports | Build spending report UI: filter by supplier, category, date range; display charts and summary tables | Y | Development | ET-In, ET-Ex | 2026-04-13 | 2026-04-14 | 100% | Mansi Bhadani
37 |  |  |  | Implement report data aggregation API: sum spend by supplier, category, and time period | Y | Development | DF-In, DF-Out, CL | 2026-04-14 | 2026-04-15 | 100% | Arun Omprakash Garwan
38 |  |  |  | Validate report filter inputs and handle date range edge cases (empty results, future dates) | Y | Development | FV | 2026-04-15 | 2026-04-15 | 100% | Kiran Subhash Rathod
39 |  |  |  | Test report accuracy against known order data; verify entitlement (retailer sees own spend only) | N | Testing | ADT | 2026-04-16 | 2026-04-16 | 100% | Om Kiran Patil
40 |  | 05.04 | Smart Reorder Suggestions | Design reorder suggestions dashboard: display recommended products with suggested quantities and suppliers | Y | Development | ET-In, ET-Ex | 2026-04-17 | 2026-04-17 | 100% | Mansi Bhadani
41 |  |  |  | Implement suggestion algorithm: analyze past order history and inventory signals to calculate reorder quantities | Y | Development | DF-In, DF-Out, CL | 2026-04-18 | 2026-04-19 | 100% | Meet Pravinbhai Mangukiya
42 |  |  |  | Test suggestion accuracy with varied order histories; verify suggestions are retailer-specific | N | Testing | ADT | 2026-04-20 | 2026-04-20 | 100% | Asmith Reddy Mamilla
43 |  | 05.05 | Subscription & Commission Calculations | Build admin UI to define subscription tiers, commission rates, and apply them to supplier accounts | Y | Development | ET-In | 2026-04-19 | 2026-04-19 | 100% | Aakash Hariprakash Varma
44 |  |  |  | Implement calculation engine: compute subscription fees and commissions based on transaction volumes | Y | Development | CL, DF-In, DF-Out | 2026-04-20 | 2026-04-20 | 100% | Meet Pravinbhai Mangukiya
45 |  |  |  | Validate subscription plan configuration: rates > 0, billing cycle fields required, no overlapping tiers | Y | Development | FV | 2026-04-21 | 2026-04-21 | 100% | Meet Pravinbhai Mangukiya
46 |  |  |  | Test commission calculations against known transaction data; verify audit trail for all billing events | N | Testing | ADT | 2026-04-21 | 2026-04-21 | 100% | Asmith Reddy Mamilla

## Sprint 3
Team 1 - Tasks for User Stories - BulkCart
Task No. | Module | RCT ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Task Type | Crosscut Reference | Start Date | End Date | % Progress | Owner
46 | 03. Product Catalog & Pricing | 03.04 | Inventory Thresholds & Alerts | Build threshold configuration UI: define minimum stock quantity and alert email per product-supplier pair | Y | Development | ET-In, ET-Ex | 2026-04-22 | 2026-04-22 | 100% | Aakash Hariprakash Varma
47 |  |  |  | Implement threshold monitoring service: poll inventory levels and dispatch alert notifications when stock falls below alertQty | Y | Development | DF-In, DF-Out, SI | 2026-04-22 | 2026-04-23 | 100% | Kiran Subhash Rathod
48 |  |  |  | Validate threshold inputs: alertQty > 0, email format valid, enforce one active threshold per product-supplier pair | Y | Development | FV, DDV | 2026-04-23 | 2026-04-23 | 100% | Arun Omprakash Garwan
49 |  |  |  | Test alert trigger conditions and audit log for threshold creation, update, and deletion events | N | Testing | ADT | 2026-04-23 | 2026-04-24 | 100% | Vivek Vekhande
50 |  | 03.05 | Product Visibility Rules | Build visibility rule config UI: assign product-level visibility to specific retailer groups with effective date | Y | Development | ET-In, ET-Ex | 2026-04-24 | 2026-04-24 | 100% | Aakash Hariprakash Varma
51 |  |  |  | Implement rule-based catalog filter: restrict product display based on retailer group assignment at browse time | Y | Development | DF-In, DF-Out | 2026-04-25 | 2026-04-25 | 100% | Meet Pravinbhai Mangukiya
52 |  |  |  | Validate visibility rule inputs: effectiveDate required, product and retailer group mandatory, prevent duplicate active rules | Y | Development | FV, DDV | 2026-04-25 | 2026-04-26 | 100% | Kiran Subhash Rathod
53 |  |  |  | Test visibility enforcement per retailer group and audit trail for rule creation and modification | N | Testing | ADT | 2026-04-27 | 2026-04-27 | 100% | Om Kiran Patil
54 | 04. Shipment & Fulfillment | 04.01 | Create Shipments | Build shipment creation UI: link approved orders, select warehouse, group line items into packages | Y | Development | ET-In, ET-Ex | 2026-04-28 | 2026-04-29 | 100% | Aakash Hariprakash Varma
55 |  |  |  | Implement shipment creation API: generate Shipment records, set initial status, emit shipment data-out event | Y | Development | DF-In, DF-Out, SI | 2026-04-29 | 2026-04-30 | 100% | Kiran Subhash Rathod
56 |  |  |  | Validate shipment data: orderId must be in approved status; warehouse and carrier fields required; quantities must match order | Y | Development | FV | 2026-04-30 | 2026-04-30 | 100% | Arun Omprakash Garwan
57 |  |  |  | Test shipment creation flow, status transitions, and audit log for every shipment lifecycle event | N | Testing | ADT | 2026-04-30 | 2026-05-01 | 100% | Asmith Reddy Mamilla
58 |  | 04.02 | Integrate Shipping Carriers | Build carrier management UI: add and edit carrier credentials, API keys, and account numbers | Y | Development | ET-In, ET-Ex | 2026-04-22 | 2026-04-24 | 100% | Aakash Hariprakash Varma
59 |  |  |  | Integrate carrier API: fetch shipping rates, generate labels, and retrieve tracking numbers via external carrier endpoints | Y | Development | DF-In, DF-Out, SI | 2026-04-25 | 2026-04-26 | 100% | Kiran Subhash Rathod
60 |  |  |  | Validate carrier configuration: API key and account number required; verify connectivity to carrier before saving | Y | Development | FV | 2026-04-27 | 2026-04-27 | 100% | Meet Pravinbhai Mangukiya
61 |  |  |  | Test carrier API integration for rate fetch, label generation, and audit log for carrier add/edit events | N | Testing | ADT | 2026-04-28 | 2026-04-28 | 100% | Vivek Vekhande
62 |  | 04.03 | Provide Delivery Tracking | Build tracking UI: display real-time shipment status and timeline events for retailers per order | Y | Development | ET-In, ET-Ex | 2026-05-03 | 2026-05-04 | 100% | Mansi Bhadani
63 |  |  |  | Implement carrier polling service: sync tracking status updates from carrier API to Shipment records | Y | Development | DF-In, SI | 2026-05-04 | 2026-05-05 | 100% | Arun Omprakash Garwan
64 |  |  |  | Validate tracking access: only the ordering retailer and authorized internal roles may view shipment tracking data | Y | Development | FV, ET-Ex | 2026-05-05 | 2026-05-05 | 100% | Kiran Subhash Rathod
65 |  |  |  | Test tracking updates with live and simulated carrier data; verify audit log entries for each status change | N | Testing | ADT | 2026-05-05 | 2026-05-06 | 100% | Om Kiran Patil
66 |  | 04.04 | Warehouse Pick | Build pick list UI for warehouse staff: display item descriptions, required quantities, and bin locations per shipment | Y | Development | ET-In, ET-Ex | 2026-05-05 | 2026-05-06 | 100% | Aakash Hariprakash Varma
67 |  |  |  | Implement pick list generation: create PickList and PickListItem records from an approved shipment on dispatch initiation | Y | Development | DF-In, DF-Out | 2026-05-06 | 2026-05-07 | 100% | Meet Pravinbhai Mangukiya
68 |  |  |  | Validate pick quantities: pickedQty must not exceed orderedQty; all items must be confirmed before shipment dispatch | Y | Development | FV | 2026-05-07 | 2026-05-07 | 100% | Arun Omprakash Garwan
69 |  |  |  | Test pick list workflow from generation through full confirmation; verify audit log for each pick confirmation action | N | Testing | ADT | 2026-05-07 | 2026-05-08 | 100% | Asmith Reddy Mamilla
70 |  | 04.05 | Delivery Exception Handling & Re-Shipment | Build exception logging UI: report failed or partial delivery, select exception type, and enter description and reference number | Y | Development | ET-In, ET-Ex | 2026-05-07 | 2026-05-08 | 100% | Aakash Hariprakash Varma
71 |  |  |  | Implement re-shipment flow: create replacement Shipment linked to original DeliveryException record and notify retailer | Y | Development | DF-In, DF-Out, SI | 2026-05-08 | 2026-05-09 | 100% | Kiran Subhash Rathod
72 |  |  |  | Validate exception records: exception type required, description mandatory, reShipmentId must reference a valid existing shipment | Y | Development | FV | 2026-05-09 | 2026-05-09 | 100% | Meet Pravinbhai Mangukiya
73 |  |  |  | Test exception logging, resolution workflow, re-shipment creation, and audit trail for all exception lifecycle events | N | Testing | ADT | 2026-05-09 | 2026-05-09 | 100% | Vivek Vekhande
74 |  | 04.06 | Shipment Documents & Labels | Build shipment document UI: view and download packing slips, invoices, and shipping labels per shipment | Y | Development | ET-In, ET-Ex | 2026-05-08 | 2026-05-09 | 100% | Mansi Bhadani
75 |  |  |  | Implement document generation service: produce packing slips and carrier labels from shipment data and store file URLs | Y | Development | DF-In, DF-Out, SI | 2026-05-09 | 2026-05-10 | 100% | Arun Omprakash Garwan
76 |  |  |  | Validate document generation requests: shipment must be in a dispatchable status before documents can be produced | Y | Development | FV | 2026-05-10 | 2026-05-10 | 100% | Kiran Subhash Rathod
77 |  |  |  | Test document generation output, download links, and audit log for each document creation event | N | Testing | ADT | 2026-05-10 | 2026-05-10 | 100% | Om Kiran Patil
78 | 05. Financial & Analytics | 05.01 | Generate Invoices | Build invoice view UI: display generated invoices per order with line items, subtotal, tax, and total | Y | Development | ET-In, CL | 2026-05-08 | 2026-05-09 | 100% | Aakash Hariprakash Varma
79 |  |  |  | Implement invoice generation service: create Invoice record from shipped/completed order; calculate subtotal, tax, and total | Y | Development | CL, DF-In, DF-Out, SI | 2026-05-09 | 2026-05-10 | 100% | Meet Pravinbhai Mangukiya
80 |  |  |  | Validate invoice data: orderId must be in shipped status, subtotal + tax must equal total, prevent duplicate invoice per order | Y | Development | DDV, CL | 2026-05-10 | 2026-05-11 | 100% | Arun Omprakash Garwan
81 |  |  |  | Test invoice generation accuracy against order data and audit log for each invoice creation and status update | N | Testing | ADT | 2026-05-11 | 2026-05-11 | 100% | Asmith Reddy Mamilla
82 |  | 05.06 | Aging & Dunning | Build aging dashboard UI: display overdue invoices grouped by aging bucket (30/60/90+ days) with outstanding amounts | Y | Development | ET-In, CL | 2026-05-09 | 2026-05-10 | 100% | Mansi Bhadani
83 |  |  |  | Implement dunning scheduler: calculate days overdue, assign aging bucket, and trigger reminder notifications for late invoices | Y | Development | CL, DF-Out, SI | 2026-05-10 | 2026-05-11 | 100% | Meet Pravinbhai Mangukiya
84 |  |  |  | Validate aging records: invoiceId must reference an unpaid invoice; daysOverdue must match computed value from dueDate | Y | Development | DDV, CL | 2026-05-10 | 2026-05-11 | 100% | Kiran Subhash Rathod
85 |  |  |  | Test aging bucket assignments, dunning trigger logic, and audit trail for all dunning notification events | N | Testing | ADT | 2026-05-11 | 2026-05-11 | 100% | Vivek Vekhande