## Team 1 - Report
Team 1: Jenkins Implementation Planning and Progress Tracking
Admin: | Aakash Varma
Sprint | Task Title | Description | Progress
PREP | Provision Host Server | Spin up a AWS EC2 to host Jenkins Server | 100%
|  | Allocate security groups | 100%
PREP | Install Jenkins and Java | Install Java JDK | 100%
|  | Install Jenkins Service | 100%
PREP | Jenkins Initial Setup | Setup Jenkins primary admin user | 100%
|  | Install default plugins | 100%
S1 | Install Required Plugins | Install NodeJs Plugin | 100%
|  | Install Github Plugin | 100%
|  | Install SSH Credentials Plugin | 100%
S1 | Configure Node.js tools | Configure global tool in jenkins and setup the specific Node.js version required for Front and Backend | 100%
S1 | Setup Env Secrets | Add DB Credentials | 100%
|  | Add JWT secrets | 100%
S1 | Github Webhook Integration | Connect Jenkins Server to the github repo | 100%
|  | SLACK: Release Notes - Story and Crosscuts to test in QA environment | 100%
|  | Jenkins/AWS - validate team member access to QA environment | 100%
|  | Configure webhook to trigger a build automatically on pushes to the dev branch | 100%
S2 | Create Jenkinsfile (Base) | Create the declarative Jenkinsfile in the root of the repo | 100%
|  | Define the initial stages | 100%
S2 | Backend Test Stages | Add stages in Jenkinsfile to navigate to /server folder | 100%
|  | run npm install and then npm test to validate Finite State Machine workflow logic | 100%
S2 | Frontend Build Stages | Add stages in Jenkinsfile to navigate to /client folder | 100%
|  | run npm run build to build compile ReactSPA | 100%
S3 | Deploy Backend and worker | Add a deployment stage to AWS | 100%