## Road Map
BulkCart
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/24/2026 | SPRINT2 - 04/21/2026 | SPRINT3 - 05/12/2026
01 User & Account Management | 01.01 Register & Authentic Users | 3 | X
| 01.02 Manage Roles & Permissions | 3 | X
| 01.03 Update Company Profiles | 2 | X
| 01.04 Manage Organization Addresses & Warehouses | 2 | X
| 01.05 Console & Navigation Access Control | 3 | X
| 01.06 Account Lifecycle Management | 3 | X
| 01.07 Notification Preferences & Routing | 3 | X
02 Order & Approval Management | 02.01 Create & Submit Purchase Orders | 3 | X
| 02.02 Manage Approval Workflow | 3 | X
| 02.03 Track Order Status & History | 2 |  | X
| 02.04 Order Drafts & Editing | 3 |  | X
| 02.05 Order Validation & Business Rules | 3 |  | X
| 02.06 Order Search & Filtering | 2 |  | X
| 02.07 Bulk Order Processing | 4 |  | X
03 Product Catalog & Pricing | 03.01 Manage Product Catalog & Inventory | 5 |  | X
| 03.02 Configure Pricing & Discounts | 3 |  | X
| 03.03 Browse & Search Product Catalog | 2 |  | X
| 03.04 Inventory Thresholds & Alerts | 3 |  |  | X
| 03.05 Product Visibility Rules | 3 |  |  | X
04 Shipment & Fulfillment | 04.01 Create Shipments | 3 |  |  | X
| 04.02 Integrate Shipping Carriers | 3 |  |  | X
| 04.03 Provide Delivery Tracking | 6 |  |  | X
| 04.04 Warehouse Pick | 2 |  |  | X
| 04.05 Delivery Exception Handling & Re‑Shipment | 4 |  |  | X
| 04.06 Shipment Documents & Labels | 2 |  |  | X
05 Financial & Analytics | 05.01 Generate Invoices | 2 |  |  | X
| 05.02 Process Payments | 3 |  | X
| 05.03 Generate Spending Reports | 2 |  | X
| 05.04 Smart Reorder Suggestions | 3 |  | X
| 05.05 Subscription & Commission Calculations | 3 |  | X
| 05.06 Aging & Dunning | 3 |  |  | X
|  | VELOCITY: | 25 | 35 | 31

## JIRA Roadmap S1
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## JIRA Roadmap S2
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## JIRA Roadmap S3
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board